## Лист1
ID | Summary | Discription | Step to reproduce | Severity | Priority | Reprodutibiliti | Simptom | Workround | Attachment | Status | Comments
B1 | Registration for a test drive in the registration form is performed with empty fields. | After confirming the contact information on page 4 with empty fields, the application proceeds to page 5. When confirming the data with the "Register" button, the entry is made. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: The recording is in progress. Expected Result: Unfilled fields are highlighted "Enter data". | 1. Go to the application. 2. Complete steps 1-2. 3. In step 4, leave the contact information fields blank. 4. In step 5 "Confirmation of data" press "Sign up" - there will be gratitude for signing up for a test drive. | Major | Normal | Always | Incorrect operation | - | https://drive.google.com/file/d/1Kja4Usw59-fpgWjC8dWEiGl-bSOAqmRf/view?usp=sharing | New | Clarify: whether the requirements specify how the application should behave in the case of empty fields.
B2 | Registration for a test drive in the registration form is performed when incorrect data is entered. | After confirming the contact information on page 4 with incorrectly entered data (using special characters, numbers, spaces), the application proceeds to page 5. When the data is confirmed with the "Register" button, the entry is made. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: The recording is in progress. Expected Result: Error "Data is invalid". | 1. Go to the application. 2. Complete steps 1-2. 3. In step 4, enter incorrect data (special characters, numbers, spaces) into the contact data entry fields. 4. In step 5 "Confirmation of data" press "Sign up" - there will be gratitude for signing up for a test drive. | Major | Normal | Always | Incorrect operation | - | https://drive.google.com/file/d/1iM0GSkXvLW5RrOkgGkPrlYMe-xhibdvS/view?usp=sharing | New | Clarify: whether the requirements specify how the application should behave in the case of incorrectly filled fields.
B3 | There are no restrictions on the entered characters in the fields of the registration form when entering data. | When filling in the fields with contact information in the registration form on page 4, it is impossible to determine the maximum number of characters to enter. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: The number is unlimited. Expected Result: Limited number of characters entered. | 1. Go to the application. 2. Complete steps 1-2. 3. In step 4, enter an unlimited number of characters in the contact data entry fields - the data is entered. | Medium | Normal | Always | Suggestion for improvement | - |  | New | Clarify: whether the requirements specify the maximum allowed number of characters to be filled in the data entry fields.
B4 | When choosing a model, a photo of a car slides down and is duplicated when switching quickly. | When the arrow is pressed intensively in any direction during the selection of the car model, the photo of the model slides down and is duplicated with a delay. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: The photo slides down and is duplicated with a delay. Expected Result: Photo in place. | 1. Go to the application. 2. Press the "Model selection" arrow intensively - the photo slides down and is duplicated with a delay. | Medium | Low | Always | Unexpected behavior | Press slower | https://drive.google.com/file/d/1D620UW48tNM03TS_ndzRoK5lTmJx81La/view?usp=sharing | New
B5 | Violation of page numbers in a test drive record when switching between pages. | After selecting the technical characteristics of the model on page 2, when moving to the next step, page 4 immediately follows. Playback: Win10, Google Chrome version 87.0.4280.66, 1920х1080 dpi. Requirement: None. Actual result: 4. Expected result: 3. | 1. Go to the application. 2. Complete 1 step "Model selection". 3. In step 2, select "Specifications". 4. Click "Continue" - page 4 appears. | Minor | Normal | Always | Cosmetic defect | - | https://drive.google.com/file/d/1HjgXogwtZG2rOe9BtqHy5wpNESqucM4z/view?usp=sharing | New | Clarify: page 3 has been deleted and the numbering is broken or a numbering error
B6 | Spelling error in the preposition after confirming the test drive registration. | Spelling error in the derived preposition "during" after confirming the entered data for recording for a test drive. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: в течении. Expected Result: в течение. | 1. Go to the application. 2. Follow steps 1-4. 3. On step 5, click "Sign up" - an entry with a spelling error appears. | Minor | Low | Always | Spelling mistake | - | https://drive.google.com/file/d/11OfbzAeRasZ8hK2vLtoby3JYuVuCo9zf/view?usp=sharing | New
B7 | There are no buttons to return to the previous step in the registration form when registering for a test drive. | During steps 1-5 when registering for a test drive, the user does not have the option to return to the previous step. In case of incorrectly entered data, the user is forced to start registration again, for example, by refreshing the page. Playback: Win10, Google Chrome version 87.0.4280.66, 1920x1080 dpi. Requirement: None. Actual result: No refunds. Expected Result: "Previous Step" button. | 1. Go to the application. 2. Complete steps 1-5 - there is no return at each step. | Minor | Low | Always | Suggestion for improvement | Perform registration carefully. Check the selected and entered data before confirming actions. |  | New | Clarify whether the requirements specify whether it is possible to return to a previous step.
ID | Summary | Discription | Step to reproduce | Severity | Priority | Reprodutibiliti | Simptom | Workround | Attachment | Status | Comments
B1 | The "Search" field on the home page does not display search results when you enter a search query. | When you enter in the field "Search", located on the main page of the site in the upper right corner, the information requested for the search, for example: Benson, as a result of the request we get: 0 search results for Benson. Playback: Win10, Google Chrome version 88.0.4324.104, 1920x1080 dpi. Requirement: None. Actual result: 0 search results for Benson. Expected Result: (count) search results for Benson. | 1. Go to the site. 2. In the "Search" field, enter Benson and click the "Search" button - 0 search results for Benson. | Major | Normal | Always | Unimplemented functionality | Do not use the "Search" field to find information on the site. | https://drive.google.com/file/d/1PDYDmKScUZXTYV6yjLbfOVa-X7RteFcu/view?usp=sharing | New | Clarify: how the site should behave when searching for information.
B2 | A help form on the site is sent when incorrect data is entered. | When filling out the help form with incorrect data (using special characters, numbers, spaces) and pressing the "SUBMIT" button, the form is filled in, a message is sent and a success message appears and thanks for filling out the form. Playback: Win10, Google Chrome version 88.0.4324.104, 1920x1080 dpi. Requirement: None. Actual result: Success! Thanks for filling out our form! Expected Result: Error! The entered data is not correct. | 1. Go to the site. 2. Select the We are Wabash tab. 3. Select any name from the list. For example: OUR HERITAGE. 4. A HOW CAN WE HELP form will appear at the bottom of the site? 5. In the input fields "Name", "Company", "Email", "Phone", "Comments" enter incorrect data (special characters, numbers, spaces). 6. Press "SUBMIT" - an entry appears: Success! Thanks for filling out our form! | Major | Normal | Always | Incorrect operation | - | https://drive.google.com/file/d/1P5GfZnszjoL5H3dpe7uEV4DBJKx8cgIB/view?usp=sharing | New | 1. Clarify: is it specified in the requirements how the site should behave in the case of incorrectly filled fields. 2. The same problem when switching to the Tradition of Innovation, Our products, Our brands, Work with Wabash tabs.
B3 | The help form on the site is sent with empty fields. | When the fields of the help form are filled in and the "SUBMIT" button is pressed, the form is filled in, sent and a success message and thanks for filling out the form appears. Playback: Win10, Google Chrome version 88.0.4324.104, 1920x1080 dpi. Requirement: None. Actual result: Success! Thanks for filling out our form! Expected Result: Empty fields are highlighted. An inscription appears: error! Enter the data. | 1. Go to the site. 2. Select the We are Wabash tab. 3. Select any name from the list. For example: OUR HERITAGE. 4. A HOW CAN WE HELP form will appear at the bottom of the site? 5. Leave the input fields "Name", "Company", "Email", "Phone", "Comments" empty. 6. Press "SUBMIT" - an entry appears: Success! Thanks for filling out our form! | Major | Normal | Always | Incorrect operation | - | https://drive.google.com/file/d/1QE1yHPMTQ2UQnbONgfNCcnQ9V0oELrBy/view?usp=sharing | New | 1. Clarify: whether the requirements specify how the site should behave in the case of empty fields. 2. The same problem when switching to the Tradition of Innovation, Our products, Our brands, Work with Wabash tabs.
B4 | The Download Product Sheet (PDF) file in the NEWS tab is blocked during download. | When you try to download the Download Product Sheet (PDF) file with a description of the product, located in the NEWS tab, information about the download blocking appears. Playback: Win10, Google Chrome version 88.0.4324.104, 1920x1080 dpi. Requirement: None. Actual result: The download is blocked. Expected Result: File downloaded. | 1. Go to the site. 2. Go to the NEWS tab. 3. In the lower right corner in the Downloads section, click on the download file Download Product Sheet (PDF) - downloads are blocked. | Medium | Normal | Always | Unimplemented functionality | Use the feedback form or telephone to contact a company representative to obtain the necessary information. | https://drive.google.com/file/d/18NBuQm6HwU-yUBagb_2dEp-A7_5PwsyY/view?usp=sharing | New | 1. Clarify: how the site should behave while downloading information. 2. The same problem is observed when in the AT-A-GLANCE section when clicking on the Review Warranties file Financing.
B5 | When you go to the social network LinkedIn, the manufacturer's page is missing. | The manufacturer page is not displayed when going to LinkedIn. the user is taken to his page. Playback: Win10, Google Chrome version 88.0.4324.104, 1920x1080 dpi. Requirement: None. Actual result: The user is taken to their page. Expected Result: Producer page. | 1. Go to the site. 2. At the bottom, select the icon of the LinkedIn network and click on it - the page of the network user is loaded. | Minor | Low | Always | Unexpected behavior | - | https://drive.google.com/file/d/19TytVTunRUhKXmpiiWYjyqoaFdDoCoDH/view?usp=sharing | New | 1. Clarify: how the site should behave when going to LinkedIn. 2. The same problem is observed when going to twitter, YouTube, facebook.
ID | Summary | Discription | Step to reproduce | Severity | Priority | Reprodutibiliti | Simptom | Workround | Attachment | Status | Comments
B1 | OFFICE HOURS says So instead of Su | Common abbreviations in English are considered Su. Reproduced on: Win 7 Actual result: " So ". Expected result: " Su ". | 1. Launch the application 2. Scroll down to OFFICE HOURS - So: closed | Minor | Low | Always | Spelling mistake | - | - | New
B2 | Non-clickable samples of drawings and plans | For clarity, it is necessary to increase the sample of drawings and a house plan.. Reproduced on: Win 7 Actual result: Common list. Expected result: Increasing the required project | 1. Launch the application 2. Click on the "Drawing&Designs" board - page with a non-clickable list of drawings and projects | Minor | Low | Always | Missing feature | - | - | New
B3 | Unclickable email button | In the Blog tab, after selecting an Architect, there are 9 ways to share the entry at the bottom of the project. Button with envelope "Share by email" is not clickable. Reproduced on: Win 7 Actual result: Not clickable. Expected result: A form for sending a message opens | 1. Launch the application 2. Click on the "Blog" board → click Architect → Scroll down to Share this entry → click on the envelope - envelope "Share by email" is not clickable | Minor | Low | Always | Missing feature | - | - | New
B4 | ОШИБКА: неверный ключ | On the "Home" page when you click on Click here to get Architect's free Drawings and FREE ARCHITECT DRAWINGS on the bottom left, a window labeled ОШИБКА: неверный ключ. Reproduced on: Win 7 Actual result: ОШИБКА: неверный ключ. Expected result: Caption Enter key | 1. Launch the application 2. Click on the "Home" board → click here to get Architect’s free Drawings → click FREE ARCHITECT DRAWINGS → scroll down - the inscription on the left in the window ОШИБКА: неверный ключ | Minor | Low | Always | Missing feature | - | - | New
ID | Summary | Discription | Step to reproduce | Severity | Priority | Reprodutibiliti | Simptom | Workround | Attachment | Status | Comments
B1 | Profile photo display | In the profile, if there is no profile photo, a human figure is displayed. Reproduse: Win 10 Actual resalt: In the profile, if there is no profile photo, a human figure is displayed. Expected resalt: A smile is displayed in the profile if there is no profile picture. | 1. Start the application. 2. Click the profile icon. | Minor | Low | Always | Cosmetic defect | - | - | New
B2 | Profile icon location | The profile menu icon is located in the main horizontal menu to the right of the Asset Classe icon. Reproduse: Win 10 Actual resalt: The profile menu icon is located in the main horizontal menu to the right of the Asset Classe icon Expected resalt: The profile menu icon is located in the main horizontal menu to the right of the Reuter Insider icon. | 1. Start the application. 2. Click the profile icon. | Minor | Low | Always | Cosmetic defect | - | - | New
B3 | Profile view | When you click on the profile icon in the main horizontal menu, a screen opens: “Unable to get profio” Reproduse: Win 10 Actual resalt: When you click on the profile icon in the main horizontal menu, a screen opens: “Unable to get profio” Expected resalt: Profile view is displayed when you click the profile icon. | 1. Start the application. 2. Click the profile icon. | Critical | Low | Always | Incorrect operation | - | - | New